## Sheet1
ITSC-3155 Software Engineering
Product Backlog
Feature Name | PRIORITY | POINTS | DEFINE USER STORY | ASSIGNED TO SPRINT | SPRINT # | WHO
Create a menu | High |  | No | Yes | 1 | Angel
New account creation | High |  |  | Yes | 1 | Alan
real-time order status | High |  | Yes | Yes | 1 | Angel
staff-side interface for orders | High |  | Yes | Yes | 1 | Angel
Use guest account | High | 8 | No | Yes | 1 | Lekhana
Data organization of trends and sales | Low |  | Yes | Yes | 1 | Alan
Edit account | Low |  |  | Yes | 1 | Lekhana
Leave a rating | Low |  | No | Yes | 2 | Anthony
Payment Processing | Low | 2 | No | Yes | 2 | Anthony
Promo codes | Low |  | Yes | Yes | 1 | Lakhana
Write a review | Low |  | No | Yes | 2 | Anthony
Log into account | Medium |  |  | Yes | 1 | Alan
Log out of account | Medium |  |  | Yes | 1 | Alan
order tracking | Medium |  | Yes | Yes | 1 | Angel
Order with account | Medium | 13 | No | Yes | 1
Api | [5 empty] | Tristan
UML/User diagrams | [5 empty] | Anthony